## Task Tracker
scopeblock — Task Tracker
For each row: set Status and % Complete as you go. 'Description' is what you must do for that activity to be Done.
Overall progress: | 0% | 0 of 12 activities Done
ID | Function | Activity (what to do) | Description — done when | Status | % Complete | Due | Notes
F1.1 | Function 1 — bench_connect.py | Set up Python environment | Install Python 3.11+, create venv (.venv) and activate it, then pip install pyvisa. Done: `python -c "import pyvisa"` runs in the venv. | Not Started | 0% | 2026-07-06
F1.2 |  | Install VISA backend | Install NI-VISA (or TekVISA) so pyvisa can reach instruments. Done: pyvisa.ResourceManager().list_resources() runs without error. | Not Started | 0% | 2026-07-06
F1.3 |  | Set SCOPE_RESOURCE | Find the scope's VISA address (USB0::0x0699::... or TCPIP0::<ip>::INSTR) and set the SCOPE_RESOURCE env var. Done: env var holds the correct string. | Not Started | 0% | 2026-07-06
F1.4 |  | Write the open/close skeleton | In scripts/bench_connect.py open ResourceManager and open_resource inside a `with` block; add argparse (--resource/--timeout) and fall back to SCOPE_RESOURCE, listing resources if unset. Done: script runs to the query step. | Not Started | 0% | 2026-07-06
F1.5 |  | Add I/O settings + hygiene + queries | Set inst.timeout and read/write terminations to '\n'; query *IDN?; send HEADer OFF / VERBose OFF / *CLS; query ALLEV?. Done: prints IDN and the error queue. | Not Started | 0% | 2026-07-06
F1.6 |  | Run on the bench + verify | Run against the real scope. Done: prints a Tektronix MSO44B identity, an empty error queue, and exits 0; with SCOPE_RESOURCE unset it lists resources. | Not Started | 0% | 2026-07-06
F2.1 | Function 2 — connect() / identify() | Define the Transport interface | In transport/base.py define the Transport Protocol (write / query / query_binary / close) and TransportError. Done: importable and typed. | Not Started | 0% | 2026-07-08
F2.2 |  | Implement VisaTransport | Wrap pyvisa (reuse F1 logic): write, query (strip), query_binary (read_raw), close; map a pyvisa timeout to TransportError. Done: *IDN? works through it. | Not Started | 0% | 2026-07-08
F2.3 |  | Build FakeTransport | In-memory transport that records writes and returns a canned *IDN?. Done: usable in a test with no hardware. | Not Started | 0% | 2026-07-08
F2.4 |  | Write MSO44B.session_setup() | Query *IDN?, send HEADer OFF / VERBose OFF / *CLS, set a _session_ready flag so it runs once. Done: returns the IDN and runs hygiene a single time. | Not Started | 0% | 2026-07-08
F2.5 |  | Offline unit test | pytest with FakeTransport: assert session_setup returns the IDN, issues hygiene in order, and is idempotent (2nd call re-runs nothing). Done: test passes. | Not Started | 0% | 2026-07-08
F2.6 |  | Bench validate | On the bench assert the IDN matches TEKTRONIX,MSO44 and the error queue is empty. Done: acceptance met with no lingering session lock. | Not Started | 0% | 2026-07-08

## Sheet 1
scopeblock — Task Tracker
For each row: set Status and % Complete as you go. 'Description' is what you must do for that activity to be Done.
Overall progress: | 0% | 0 of 42 activities Done
ID | Function | Activity (what to do) | Description — done when | Status | % Complete | Due | Notes
F1.1 | Function 1 — bench_connect.py | Set up Python environment | Install Python 3.11+, create venv (.venv) and activate it, then pip install pyvisa. Done: `python -c "import pyvisa"` runs in the venv. | Not Started | 0% | 2026-07-06
F1.2 |  | Install VISA backend | Install NI-VISA (or TekVISA) so pyvisa can reach instruments. Done: pyvisa.ResourceManager().list_resources() runs without error. | Not Started | 0% | 2026-07-06
F1.3 |  | Set SCOPE_RESOURCE | Find the scope's VISA address (USB0::0x0699::... or TCPIP0::<ip>::INSTR) and set the SCOPE_RESOURCE env var. Done: env var holds the correct string. | Not Started | 0% | 2026-07-06
F1.4 |  | Write the open/close skeleton | In scripts/bench_connect.py open ResourceManager and open_resource inside a `with` block; add argparse (--resource/--timeout) and fall back to SCOPE_RESOURCE, listing resources if unset. Done: script runs to the query step. | Not Started | 0% | 2026-07-06
F1.5 |  | Add I/O settings + hygiene + queries | Set inst.timeout and read/write terminations to '\n'; query *IDN?; send HEADer OFF / VERBose OFF / *CLS; query ALLEV?. Done: prints IDN and the error queue. | Not Started | 0% | 2026-07-06
F1.6 |  | Run on the bench + verify | Run against the real scope. Done: prints a Tektronix MSO44B identity, an empty error queue, and exits 0; with SCOPE_RESOURCE unset it lists resources. | Not Started | 0% | 2026-07-06
F2.1 | Function 2 — connect() / identify() | Define the Transport interface | In transport/base.py define the Transport Protocol (write / query / query_binary / close) and TransportError. Done: importable and typed. | Not Started | 0% | 2026-07-08
F2.2 |  | Implement VisaTransport | Wrap pyvisa (reuse F1 logic): write, query (strip), query_binary (read_raw), close; map a pyvisa timeout to TransportError. Done: *IDN? works through it. | Not Started | 0% | 2026-07-08
F2.3 |  | Build FakeTransport | In-memory transport that records writes and returns a canned *IDN?. Done: usable in a test with no hardware. | Not Started | 0% | 2026-07-08
F2.4 |  | Write MSO44B.session_setup() | Query *IDN?, send HEADer OFF / VERBose OFF / *CLS, set a _session_ready flag so it runs once. Done: returns the IDN and runs hygiene a single time. | Not Started | 0% | 2026-07-08
F2.5 |  | Offline unit test | pytest with FakeTransport: assert session_setup returns the IDN, issues hygiene in order, and is idempotent (2nd call re-runs nothing). Done: test passes. | Not Started | 0% | 2026-07-08
F2.6 |  | Bench validate | On the bench assert the IDN matches TEKTRONIX,MSO44 and the error queue is empty. Done: acceptance met with no lingering session lock. | Not Started | 0% | 2026-07-08
F3.1 | Function 3 — configure(config) | Write the ScopeSetup model | pydantic model: channel, vertical scale/offset, coupling, sample_rate/horizontal_scale, record_length, trigger_source/level/slope, encoding, byte_width. Done: validates a sample config. | Not Started | 0% | 2026-07-10
F3.2 |  | Build the configure() SCPI sequence | Send vertical -> horizontal -> trigger -> transfer via a send() helper, skipping None fields; return AppliedState with the command log. Done: emits the correct SCPI and calls check_errors(). | Not Started | 0% | 2026-07-10
F3.3 |  | Offline unit test | FakeTransport records writes; assert the exact SCPI strings and their order for a known ScopeSetup, and that None fields emit nothing. Done: test passes. | Not Started | 0% | 2026-07-10
F3.4 |  | Bench validate | Apply a setup, query a value back (e.g. HORizontal:RECOrdlength?) and assert it matches; ALLEV? empty. Done: read-back matches the config. | Not Started | 0% | 2026-07-10
F4.1 | Function 4 — acquire(timeout) | Single-sequence acquire | Write ACQuire:STOPAfter SEQuence then ACQuire:STATE RUN, and block on *OPC? until the capture completes. Done: returns after a capture. | Not Started | 0% | 2026-07-13
F4.2 |  | Timeout / no-trigger handling | Wrap *OPC? in try/except TransportError -> raise AcquireTimeout; validate the '1' reply. Done: a no-trigger raises a typed error and never hangs. | Not Started | 0% | 2026-07-13
F4.3 |  | Offline unit test | Fake: *OPC?='1' + synthetic CURVe? -> a Waveform; a fake that raises TransportError -> AcquireTimeout. Done: both tests pass. | Not Started | 0% | 2026-07-13
F4.4 |  | Bench validate | With the AFG driving a signal, acquire returns a Waveform; with no trigger it raises AcquireTimeout within the timeout. Done: acceptance met. | Not Started | 0% | 2026-07-13
F5.1 | Function 5 — read_waveform(source) | Read the preamble | Query WFMOutpre fields individually (XINCR, XZERO, PT_OFF, YMULT, YOFF, YZERO, NR_PT, BYT_NR, BN_FMT, BYT_OR, units). Done: a populated Preamble object. | Not Started | 0% | 2026-07-17
F5.2 |  | Parse IEEE block + decode codes | Strip the #<n><len> header; choose the numpy dtype from sign / byte-order / width; np.frombuffer to integer codes. Done: codes decode correctly. | Not Started | 0% | 2026-07-17
F5.3 |  | Apply the affine transform | v=(code-YOFF)*YMULT+YZERO; t=XZERO+(n-PT_OFF)*XINCR; store the preamble in meta. Done: a Waveform in volts/seconds. | Not Started | 0% | 2026-07-17
F5.4 |  | Offline round-trip test | Synthesize codes + a known preamble; assert volts/time match the formula exactly; test the IEEE parser and dtype selection. Done: exact round-trip passes. | Not Started | 0% | 2026-07-17
F5.5 |  | Bench validate | Capture a known AFG level; assert volts within tolerance and len(v)==NR_PT; confirm the PT_OFF sign near the trigger. Done: acceptance met. | Not Started | 0% | 2026-07-17
F6.1 | Function 6 — measure(wf, kind) | Robust levels + amplitude | signal_levels via a histogram split about the median with a percentile fallback (never raw min/max); Vpp, mean, rms. Done: correct levels on a synthetic signal. | Not Started | 0% | 2026-07-22
F6.2 |  | Schmitt edge detection | Hysteresis states + interpolated mid-level crossings -> rising/falling edge times. Done: no double-counting on a noisy signal. | Not Started | 0% | 2026-07-22
F6.3 |  | Timing features + dispatch | period (rising-edge diffs), frequency, duty (high-time/period), rise/fall (10-90%), edge count; a name->function dispatch. Done: every kind returns. | Not Started | 0% | 2026-07-22
F6.4 |  | Offline unit test | Synthetic signals with known freq/duty/levels via pytest.approx; parametrize duty 20/40/75%; flat and noisy edge cases. Done: tests pass. | Not Started | 0% | 2026-07-22
F7.1 | Function 7 — compare(wf, expected, tol) | Tolerance + band | Tolerance(abs/rel/min/max); band() takes the wider of abs and rel, with explicit min/max overriding. Done: band math correct. | Not Started | 0% | 2026-07-25
F7.2 |  | Result + compare engine | Result(measured/expected/lower/upper/passed/units/requirement_id) + error / error_pct; compare and compare_all. Done: verdict and fields populated. | Not Started | 0% | 2026-07-25
F7.3 |  | Offline unit test | Pass and fail paths; abs-vs-rel wider-wins; min/max override; error_pct with expected=0 -> nan. Done: tests pass. | Not Started | 0% | 2026-07-25
F8.1 | Function 8 — export(wf, path, fmt) | CSV + npz export | csv (time,volts + a commented meta header) and npz (lossless arrays + meta). Done: both files write. | Not Started | 0% | 2026-07-27
F8.2 |  | load_waveform reload | Reload npz (lossless) and csv into an identical Waveform shape. Done: round-trip equal to the original. | Not Started | 0% | 2026-07-27
F8.3 |  | MF4 export (optional) | Lazy-import asammdf; raise a clear error if it is missing. Done: MF4 writes, or skips cleanly when asammdf is absent. | Not Started | 0% | 2026-07-27
F8.4 |  | Offline unit test | npz/csv round-trip equal; unsupported fmt -> ValueError; MF4 via pytest.importorskip. Done: tests pass. | Not Started | 0% | 2026-07-27
F9.1 | Function 9 — check_errors() | Surface instrument errors | Read *ESR?; if the error bits (0b0011_1100) are set, read ALLEV? and raise ScopeError with the text. Done: raises on an instrument error. | Not Started | 0% | 2026-07-29
F9.2 |  | Offline unit test | Fake ESR with an error bit -> ScopeError with the text; a clean ESR -> no raise. Done: tests pass. | Not Started | 0% | 2026-07-29
F9.3 |  | Bench validate | Send a deliberately bad command; assert check_errors raises; confirm *CLS clears the queue. Done: acceptance met. | Not Started | 0% | 2026-07-29
INT.1 | Integration — tie it together | api.py public surface | Expose configure/acquire/load/measure/compare/export + measure_all + run_test_case + self_test. Done: api importable; signatures stable. | Not Started | 0% | 2026-08-04
INT.2 |  | AFG loopback self-test (hardware) | Drive a known AFG signal, capture it, run measure+compare. Done: commanded frequency/amplitude/duty returned within tolerance on the bench. | Not Started | 0% | 2026-08-04
INT.3 |  | Reporting + docs | pytest --junitxml emits requirement->verdict evidence (optional Robot suite); update docs. Done: unattended run produces a traceable report. | Not Started | 0% | 2026-08-04